## Overzicht per umc
Telemonitoring vitale functies | UMCU | [11 empty] | LUMC | [11 empty] | Radboudumc | [11 empty] | UMCG | [11 empty] | MUMC+ | [11 empty] | AMC | [11 empty] | VUMC | [11 empty] | ErasmusMC | [12 empty] | Legenda
Doelen | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | 2019 |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  | √ | afgerond
| Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 |  | op schema
Stakeholder analyse en draagvlak | [97 empty] | achter op schema | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2019 Q4 to 2021 Q4; 2019 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2
Multidisciplinair projectteam | [97 empty] | uit fase | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2019 Q4 to 2021 Q4; 2020 Q1 to 2022 Q2; 2019 Q4 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q3 to 2022 Q2
Nulmeting (uptake zie definities) | [97 empty] | niet van toepassing | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q2 to 2022 Q2; 2020 Q3 to 2021 Q2
Workflow omschrijving huidige proces | [97 empty] | staat gepland | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q2 to 2022 Q2; 2020 Q3 to 2022 Q2
Voorbereiding gesprekken koppeling EPD | [97 empty] | volgt in de toekomst | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q3 to 2022 Q2
Verkenning (en zo mogelijk afspraken) leveranciers | [97 empty] | umc waar het project gestart is tijdens Citrien-1 | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q2 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q3 to 2022 Q2
Opstellen patientinformatie | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q1 to 2020 Q2; 2020 Q4 to 2022 Q2; 2021 Q1 to 2021 Q4; 2020 Q3 to 2022 Q2
Werkinstructies / protocollen voor zorgverleners opstellen | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q2 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q1 to 2022 Q2; 2021 Q1 to 2021 Q4; 2020 Q3 to 2022 Q2
Deelname wetenschappelijk onderzoek verkend | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q1 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q1 to 2022 Q2; 2020 Q3 to 2022 Q2
Inventarisatie resources en middelen (FINANCIEN) | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q2 to 2022 Q2; 2020 Q2 to 2021 Q4; 2020 Q2 to 2020 Q4; 2021 Q2 to 2022 Q2; 2020 Q2 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2
Voorlichten professionals | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q2 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q3 to 2022 Q2; 2020 Q2 to 2022 Q2; 2021 Q1 to 2022 Q2; 2020 Q3 to 2022 Q2
Uitwerken pilot opzet | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2021 Q4; 2019 Q4 to 2022 Q2; 2020 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2020 Q3 to 2022 Q2
Indien deelname wetenschappelijk onderzoek: voorbereiden | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2021 Q4; 2020 Q2 to 2022 Q2; 2021 Q1 to 2021 Q4; 2020 Q3 to 2022 Q2
Schrijven richtlijn/mission statement | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2020 Q3; 2021 Q1 to 2021 Q4; 2020 Q1 to 2021 Q1; 2021 Q1 to 2021 Q4; 2021 Q1 to 2021 Q4; 2020 Q3 to 2022 Q2
Inventarisatie opschaling in regio | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2022 Q2; 2021 Q3; 2021 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2022 Q2
Voorbereiden koppeling EPD | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q1 to 2022 Q2; 2019 Q4 to 2020 Q2; 2021 Q3 to 2021 Q4; 2020 Q2 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2
Projectplanning klaar | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q2 to 2022 Q2; 2021 Q1 to 2021 Q4; 2020 Q1 to 2020 Q2; 2021 Q1 to 2022 Q2; 2020 Q3 to 2022 Q2; 2020 Q3 to 2022 Q2
Start patientinclusie | bar: 2021 Q3 to 2022 Q2; 2019 Q4 to 2020 Q2; 2020 Q1 to 2020 Q2; 2021 Q1; 2021 Q3 to 2022 Q2
Afspraken inkoop | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2; 2020 Q3 to 2022 Q2
Afspraken verzekeraar | bar: 2019 Q3 to 2022 Q2; 2019 Q4 to 2022 Q2; 2020 Q4 to 2022 Q1; 2021 Q3; 2020 Q4 to 2022 Q2; 2020 Q4 to 2022 Q2; 2021 Q1 to 2022 Q1
Cijfers over opschaling monitoren | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2022 Q2; 2020 Q2 to 2022 Q1; 2021 Q2 to 2022 Q2; 2021 Q1 to 2022 Q2; 2021 Q1 to 2021 Q2
Klinische implementatie | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2022 Q2; 2020 Q2 to 2022 Q2; 2021 Q4 to 2022 Q2; 2021 Q4 to 2022 Q2; 2021 Q1 to 2022 Q2; 2021 Q1 to 2022 Q2
Evaluatie en advies eventuele bredere uitrol | bar: 2019 Q3 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q4 to 2022 Q2; 2021 Q1 to 2021 Q4; 2021 Q1 to 2021 Q3
nieuw doel (ook alvast voor Q1 Q2 en Q3 2021 invullen)
nieuw doel (ook alvast voor Q1 Q2 en Q3 2021 invullen)
nieuw doel (ook alvast voor Q1 Q2 en Q3 2021 invullen)
Note on BM5: H.J.H. Gijsbers: Actiepunt: Teams-meeting IM Ellen Maij/ICT/Preckel/Lieshout/Scwartz/Nynke/Marlies/Valesca/
Note on BN5: H.J.H. Gijsbers: meeting geweest. 2 pleisters mogen door.
Note on BO5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/12 meeting projectteam
Note on BN6: H.J.H. Gijsbers: kwantitatief is binnen. Kwalitatief geen reacties
Note on CB6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nulmeting is afgerond, maar er is geen respons
Note on BN8: H.J.H. Gijsbers: toezegging door ICT dat infrastructuur en koppeling met EPIC voor 2 verschillende pleisters.
Note on BT13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nieuwe pleister healthdot geintroduceerd door philips. opnieuw bekijken of dit een oplossing is voor AmsterdamUMC
Note on BU13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Nieuwe pleister healthdot geintroduceerd door philips. opnieuw bekijken of dit een oplossing is voor AmsterdamUMC
Note on BN14: H.J.H. Gijsbers: uitgesteld tot we zeker weten dat koppeling guardian en EPIC is gemaakt
Note on BP16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: studie sensium afronding. Guardian geen onderzoek, alleen zorginnovatie
Note on S17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Trekker van dit initiatief vanuit Radboud UMC heeft dit on hold gezet
Note on BT20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Time out. Nieuwe planning deze maand
Note on Y22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dergelijke afspraken kunnen pas worden gemaakt na afronding van de pilot. Idem voor afspraken met verzekeraar.
Note on AG23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: interne financiering is afgesproken met RvB
Note on AC24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: alleen aantal bedden is bekend

## Legenda
Legenda
√ | afgerond
op schema
achter op schema
uit fase
niet van toepassing
staat gepland
volgt in de toekomst
umc waar het project gestart is tijdens Citrien-1

## Definitie begrippen
Begrippen | Definities :
Stakeholder analyse en commitment: | Inzicht in betrokken partijen, hun rol, invloed en wensen.
Multidisciplinair projectteam: | Het uitvoerend projectteam. Dit is het projectteam, aangevuld met bijv. direct betrokken artsen, verpleegkundigen, ICT’ers, etc.
Workflow analyse van het huidige proces/zorgpad: | Analyse van de huidige werkwijze rondom het betreffende zorgpad / het betreffende concept.
Nulmeting: | Hoe groot is de patiëntpopulatie die het nieuwe zorgconcept reeds ontvangt? Hoe groot is de patiëntpopulatie is die in aanmerking zou kunnen komen voor het nieuwe zorgpad.
Werkinstructies/protocollen opstellen | Benodigde protocollen opstellen voor nieuwe werkwijze bij bijbehorend nieuw / aangepast zorgpad n.a.v. het concept dat wordt geïmplementeerd.

## Overzicht (kopie versie april)
| UMCU |  |  |  |  | LUMC |  |  |  |  | Radboudumc |  |  |  |  | UMCG |  |  |  |  | MUMC+ |  |  |  |  | AMC |  |  |  |  | VUMC |  |  |  |  | ErasmusMC | [5 empty] | Legenda
Doelen | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | 2019 |  | 2020 |  |  | √ | afgerond
| Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 | Q3 | Q4 | Q1 | Q2 | Q3 |  | op schema
Stakeholder analyse en draagvlak | √ | √ | √ | √ | √ |  | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | √ | √ | √ | √ | √ | √ | √ | √ | √ |  | √ | √ | √ | √ | [11 empty] | achter op schema
Multidisciplinair projectteam | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ |  |  |  |  | √ |  |  |  | √ | [17 empty] | uit fase
Nulmeting (uptake zie definities) | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ |  |  |  | √ | [22 empty] | niet van toepassing
Workflow omschrijving huidige proces | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ |  |  |  | √ | [22 empty] | toekomstige planning
Voorbereiding gesprekken koppeling EPD | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ | [26 empty] | umc waar het project gestart is tijdens Citrien-1
Verkenning (en zo mogelijk afspraken) leveranciers | √ | √ | √ | √ | √ | [18 empty] | √
Opstellen patientinformatie | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ |  |  |  |  | √ |  |  |  | √
Werkinstructies / protocollen voor zorgverleners opstellen | √ | √ | √ | √ | √ | [5 empty] | √ | √ | √ | √ | √ |  |  |  |  | √
Deelname wetenschappelijk onderzoek verkend | √ | √ | √ | √ | √ | [7 empty] | √ | √ | √
Inventarisatie resources en middelen | [19 empty] | √
Voorlichten professionals
Uitwerken pilot opzet
Indien deelname wetenschappelijk onderzoek: voorbereiden
Schrijven richtlijn/mission statement
Inventarisatie opschaling in regio
Voorbereiden koppeling Epic
Projectplanning klaar
Start patientinclusie